Ionospheric Challenges for LOFAR
LOFAR Status
James M Anderson
anderson@mpifr-bonn.mpg.de
On behalf of the LOFAR collaborationΐ
ΐRequired for all LOFAR presentations using commissioning data


---
Effelsberg LOFAR Station

---
Low Band
- Groundplane plastic sheets repaired
- A few receiver units replaced

---
HBA
- Tiles installed during July
- Many thanks to all involved
- Electronics validation (replacing bad parts) in early October
- A full-sky image from the HBA should be available within hours
  - If I didn't have to attend so many ****** meetings...

---
Network
- Reasonable connection to Groningen finally realized in August
- LOFAR International network meeting in Frankfurt on Sep 15
- After some problems with bandwidth, VLANs, and so on, we switched over to a full 10 GE connection from Ef to Bn
- Curently connected to Groningen and LOFAR Blue Gene for normal LOFAR operations
  - At least, whenever they haven't done something to break the connection
- Continual spec change on network design and requirements

---
Ef Pulsar Observations
Used to confirm operation of network connection

---
Long Baseline Fringes
- Ef—Ex fringes detected Aug/Sep
- Press release on MPIfR web page
  - Although not from the Aktuelles/Pressemitteilungen links

---
LOFAR Status

---
My View of the Dutch Stations

---
The Good, The Bad, and the Ugly
- Since the spring:
- Stations on the ground, connected to Groningen
- First pulsar measurements from real LOFAR stations
- First fringes from LOFAR stations
- First images from LOFAR stations
- But there are huge delays
- Only a handful of stations available
- Software development slow

---
LAD Meeting Three Weeks Ago
- Rate of bug fixes constant, while rate of new bugs reported is increasing
- “Busy Weeks” placing too large of a strain on the Dwingeloo technical/software groups
  - Must back off on busy weeks
- Many necessary commissioning tasks have not been done because the software is not yet available and/or the hardware is not yet in place
- MS3 delayed until at least 2010 March
- LAD agreement to give highest priority to getting ready for MS3
  - Tasks, development, commissioning, personnel time allocations which conflict with MS3 put on hold

---
Software Update
Some of the Many Reasons MS3 is Delayed
- MS^3 delayed to March 2010
- Necessary
  - stations
  - facet correction
  - beam model
  - ionosphere model
  - bandpass correction
  - A-team subtraction
  - clock correction

---
LOFAR Proposal Cycle 0
- Deadline was during the night of 2009 Sep 30
- Two proposal types requested
  - Cat I (Early Access) commissioning proposals
  - Cat II (Long Term) guaranteed access, KSP science submissions
- 96 proposals received
  - Initial estimate: factor of 10 oversubscription (may come down as piggybacking and subarray processing possibilities investigated)
- Technical Review Committee formed
  - 10 people (2 external to ASTRON)
  - Will review technical details of proposals, discuss at 2009 Nov 02 meeting
- LOFAR Program Committee (TAC) being formed
  - Up to 16 people, partially taken from Westerbork PC
  - Will meet in early December